## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N15E017 |  | Project Name: |  | Event Center on University
NPDES Id. No. | NMR1006MH |  | Location: |  | 1611 Airtech Ct SE
2025-03-07 |  | Owner |  |  |  | Contractor
Operator |  | Sergio and Azucena Valles
Contact name & title |  | Nolberto Trevizo
e-mail |  | beto@lindomexicogrill.com
Contact Phone # |  | 505-288-4394
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | clear
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Clear/ Windy
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 55 |  |  | Windy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Cloudy
Item Number | Deficiency/ Corrective Action | [10 empty] | Sleet
1 | The SWPPP and self-inspection reports were not available at the time of the inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of the SWPPP and all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
2 | BMPs - The inlet protection for the storm drain inlet is insufficient and does not prevent sediment from entering the City storm sewer system in violation of CGP Part 2.1.2. The installed protection does not allow for ponding water, and stormwater can bypass the protection. A stabilized construction entrance was not installed, and the dirt ramp in the curb is not allowed in violation of CGP Part 2.2.4. Required mitigation: Design and install all stormwater controls in accordance with good engineering practices, including all applicable design standards per CGP Part 2.1.2. Use appropriate stabilization techniques at all points that exit onto paved roads per CGP Part 2.2.4.b.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 3/3/2025 via email
Notes:
The electronic SWPPP was reviewed. Ensure that the SWPPP on-site includes the following: The SWPPP certification of the operators, the proper NOIs, the correct posting information, the proper Delegation of Authorities (if needed) since the EPA does not allow the delegation to be for a third party (Caldon Seeding), the identity of the operator that has day-to-day operational control (general contractor), training certificates for the SWPPP designer and inspectors, and a copy of the 2022 CGP.
The EPA requires temporary or permanent stabilization measures to be installed if land disturbances are in active for 14 or more calendar days per CGP Part 2.2.14.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action