## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N15E017 |  | Project Name: |  | Event Center on University
NPDES Id. No. | NMR1006QG |  | Location: |  | 1611 Airtech Ct SE
2025-12-01 |  | Owner |  |  |  | Contractor
Operator |  | Sergio and Azucena Valles
Contact name & title |  | Nolberto Trevizo
e-mail |  | beto@lindomexicogrill.com
Contact Phone # |  | 505-288-4394
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | clear
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Clear/ Windy
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 45 |  |  | Windy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-11-20 |  |  |  | Cloudy
Item Number | Deficiency/ Corrective Action | [10 empty] | Sleet
1 | The SWPPP has not been certified by the operators in violation of CGP Part 7.2.10. There were no self-inspection reports available on-site in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2 | BMPs - Erosion on the west slope and property line has started undercutting the perimeter silt fence, which has discharged sediment onto the neighboring property in violation of CGP Parts 2.1.4 and 2.2.3. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4. After a storm event, if there is evidence of stormwater circumventing or undercutting the perimeter control, extend controls and/or repair undercut areas to fix the problem per CGP Part 2.2.3.c.ii.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | N/A
Notes:
Sediment from erosion is building up on the western silt fence and should be properly maintained. The SWPPP is in a lock-box (Code: 0000)
The EPA requires temporary or permanent stabilization measures to be installed if land disturbances are in active for 14 or more calendar days per CGP Part 2.2.14.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action