## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | N15E017 |  | Project Name: |  | Event Center on University
NPDES Id. No. | NMR1006QG |  | Location: |  | 1611 Airtech Ct SE
2026-01-27 |  | Owner |  |  |  | Contractor
Operator |  | Sergio and Azucena Valles
Contact name & title |  | Nolberto Trevizo
e-mail |  | beto@lindomexicogrill.com
Contact Phone # |  | 505-288-4394
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1:30pm |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | clear
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Clear/ Windy
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 50 |  |  | Windy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-01-08 |  |  |  | Cloudy
Item Number | Deficiency/ Corrective Action | [10 empty] | Sleet
1 | SWPPP - There were no self-inspection reports available on-site for review in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2 | Stabilization - The land disturbance has not been permanently or temporarily stabilized for over 14 days of construction inactivity in violation of CGP Part 2.2.14. Required mitigation: Initiate the installation of stabilization measures immediately in any areas of ezposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days and complete the installation of stabilization measures as soon as practicable, but no later than 14 calendar days per CGP Part 2.2.14.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes: | The SWPPP is in a lock-box (Code: 0000)
There was no effort to prevent more erosion of the slope and sediment accumulation at the perimeter silt fence. The site's 3.7 acres drain to one low-lying point at the western perimeter.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action