## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | P09E002D_CV |  | Project Name: |  | Ceja Vista Unit 1
NPDES Id. No. | NMR1002BE |  | Location: |  | 9800 Dsennis Chavez SW
2021-01-22 |  | Dennis Chavez |  |  |  | Contractor
Operator |  | Ceja Vista LLC |  |  |  | Franklins
Contact name & title |  | Bill Allen manager |  |  |  | Gus Harbaugh
e-mail |  | ballen@westpacnm.com |  |  |  | Gus.Harbaugh@feinm.com
Contact Phone # |  | 505-440-7262 |  |  |  | w796-5457 m975-2864
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 3pm |  |  |  | Rain
Construction Phase: |  | infrastructure complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2020-12-11 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Silt fence down and full of sediment reset all and add more along Dennis Chaves
2 | Remove sediment from street and sidewalk.
3 | Inlet protection needs maintenance
4 | Stabilize all disturbed areas
5 | Provide self inspection reports
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-02-12
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action