## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | P09E002D_CV |  | Project Name: |  | Ceja Vista Unit 1
NPDES Id. No. | NMR1002BE |  | Location: |  | 9800 Dennis Chavez SW | [5 empty] | ballen@westpacnm.com
2021-06-21 |  | Owner |  |  |  | Contractor
Operator |  | Ceja Vista, LLC |  |  |  | Franklins
Contact name & title |  | Bill Allen - Manager |  |  |  | Gus Harbaugh
e-mail |  | ballen@westpacnm.com |  |  |  | Gus.Harbaugh@feinm.com
Contact Phone # |  | 505-440-7262 |  |  |  | 505-975-2864
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 10:55 AM-11:10 AM |  |  |  | Rain
Construction Phase: |  | Inactive/temporary stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  |  |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 84 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | No NOI posting. Post signage of NOI permit coverage in a location clearly visible to the public. | [9 empty] | 2021-05-03
2 | Areas appear to not be stabilized. Implement temporary stabilization measures. | [9 empty] | 2021-05-31
3 | Self-inspection reports not provided upon last request dated 6/8/2021.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-02-12
Notes: | Inspections Plus was on site working. They had repaired the silt fence prior to the inspection.
They were actively sweeping the streets and shoveling the sediment out of the gutters. They had
started cleaning around the inlets. The crew member was not aware of any plans to begin stabilization.
NOI posting was not up. Upon returning to the site on 6/22/2021, the streets and inlet protection were
cleaned. The NOI posting was still not up.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action