## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | P09E002G |  | Project Name: |  | Ceja Vista Apartments Phase 2
NPDES Id. No. | NMR10032D |  | Location: |  | Dennis Chavez and Jaguar
2023-06-13 |  | Owner |  |  |  | Contractor
2023-06-26 |  | DBG Properties, LLC |  |  |  | Trevco, Inc.
Contact name & title |  | Todd Coleman |  |  |  | Trevor Wisman
e-mail |  | todd@dbgpropertiesllc.com |  |  |  | Trevor@Trevco-inc.com
Contact Phone # |  | 505-269-7481 |  |  |  | 505-238-6215
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 10am |  |  |  | Rain
Construction Phase: |  | CO, stabilization in progress | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Waste drums with no lids are outside storage/staging area on wooden pallets on neighboring property. Section 2.3.3.c.ii of the CGP requires chemical containers to be water-tight and closed, sealed, and secured when not being actively used. This section also states that you must provide cover or secondary containment for these containers and have a spill kit available.
2 | There was no posting in a safe and public view during inspections. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of- way per CGP 1.5.
3 | No SWPPP was available at the time of inspection. The SWPPP including Self Inspection Reports and Corrective Action Reports must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
4 | In accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date:
Notes:
Current self-inspection reports have been obtained.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action