## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | P09E002G |  | Project Name: |  | Ceja Vista Senior Apartments
NPDES Id. No. | NMR10032D |  | Location: |  | 10001 Ceja Vista Rd. SW
2021-06-04 |  | Owner |  |  |  | Contractor
Operator |  | DBG Properties, LLC |  |  |  | Trevco, Inc.
Contact name & title |  | Todd Coleman |  |  |  | Trevor Wismann
e-mail |  | todd@dbgpropertiesllc.com |  |  |  | Trevor@Trevco-inc.com
Contact Phone # |  | 505-269-7481 |  |  |  | 505-238-6215
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 9:55 AM-10:40 AM |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 76 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Track-out pad needs maintenance. Modify track-out pad to prevent additional sediment from exiting the site and remove accumulated sediment., | [9 empty] | 2021-05-03
2 | Sediment blowing onto adjacent property. Add additional sediment control BMP (silt fence) along East wall to achieve the minium height of 2 feet above grade. | [9 empty] | 2021-05-31
3 | Significant erosion at SE corner of site. Install stabilized construction entrance per the ESC Plan.
4 | Hole in silt fence at North perimeter. Repair and maintain silt fences.
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Received | Latest report Date: |  | 2021-06-04
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action