## 04.2019Form
|  | City of Albuquerque ---Stormwater Construction Site Inspection Report--- | [8 empty] | Weather: | Discharge: | Reports: | ROW:
General Information | [11 empty] | Shadow | Yes
ESC File # | P09E004 |  | Project Name: |  |  | Tierra Linda Apartments | [5 empty] | Yes | No
ABQ-PLAN # | SWQ-2025-00036 |  | Location: |  |  | 9801 Ceja Vista Rd SW | [6 empty] | Electronic
NPDES ID # | NMR1007A3 | [10 empty] | No | Requested | Sidewalk
2026-03-04 |  | Owner |  |  |  |  | Contractor |  |  |  | Snow |  | Out-of-date | Street
Operator |  | DBG Properties |  |  |  |  | Gatekeeper Construction Inc |  |  |  | Clear |  | Unsigned | Storm Drain Inlet
Contact name & title |  | Eric Grodahl |  |  |  |  | Paul Ochs |  |  |  | Rain |  |  | Drainage Ditch
Contact e-mail |  | egrodahl@dbgpropertiesllc.com |  |  |  |  | paul@gatekeeperconst.com |  |  |  | Clear/Windy |  |  | Arroyo
Contact Phone # |  | 503-860-3298 |  |  |  |  | 623-433-6438 |  |  |  | Windy |  |  | Private Property
COA Inspector |  | Chancellor English |  |  |  |  | Start/End Time: |  | 12pm |  | Cloudy |  |  | N/A
Construction Phase: |  | Foundations, verticals | [8 empty] | Sleet
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | Follow Up
Weather at time of inspection: |  |  |  | Clear |  | Temperature: ~ |  | 60
Estimated date of last storm 0.25" or greater: |  |  |  |  | 2026-01-08
Item Number | Deficiency/ Corrective Action
1 | BMPs - The inlet protection for the storm drain inlets in and around the intersection of 98th St and Ceja Vista Rd SW needs cleaning and maintenance in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
2 | Washout - The concrete washout container is overloaded and leaking in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Discharge off-site? |  | No | Right-of-way: |  |  | N/A
Self-Inspection Reports? |  | Electronic | Latest report Date: |  |  | 2026-02-23
Notes:
The SWPPP is in the construction office across Ceja Vista Rd from the site.
The construction support area has been stabilized prior to construction use.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action