## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Jabil/Ethicon South Arroyo Drainage Improvements
Location: |  | 3801 University Blvd SE
Site Contact Name & Agency |  | Sonya Woodhouse Facility Manager |  |  |  | ESC File No. | P15E003
|  | sonya_woodhouse@jabil.com |  |  |  | NPDES Id. No. | NMR1002UF
Inspection Date: |  | 2020-08-04 | Start/End Time: |  | 8:15AM
CoA Stormwater Inspector: |  |  | Doug Hughes
Construction Phase: |  | Infrastructure Construction | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  |  | Temperature: ~ |  |  | 78 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [8 empty] | 2020-07-28 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NPDES coverage is out of date. An NOI and SWPPP are needed to extend the NPDES permit.
2 | No progress on Final stabelization, several large bare patches remain.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [7 empty] | No
3 | Self Inspection Reports |  |  |  |  | Latest report Date: |  | 2020-07-09
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action