## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | Q16E5000A |  | Project Name: |  | Kairos Power
NPDES Id. No. | NMR1004XE |  | Location: |  | 5201 Hawking Dr SE
2023-08-02 |  | Owner |  |  |  | Contractor
Operator |  | Kairos Power |  |  |  | Craft Contracting
Contact name & title |  | Lara Gutierrez |  |  |  | Jamie Morrison
e-mail |  | gutierrez@kairospower.com |  |  |  | jmorrison@craftcon.com
Contact Phone # |  | 510-808-5265 |  |  |  | 760-678-8016
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | foundations, vertical structure | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Posting of permit coverage was missing. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5.
2 | The SWPPP and self-inspection reports are not current and up-to-date. The SWPPP has not been certified. The Landscape Plan in the SWPPP is not current as it is for Phase 1 and not the phase currently ongoing. The last self-inspection report observed was 9/1/22. Required mitigation: Your signatory must sign and date your SWPPP in accordance with CGP Appendix G, Part G.11 as per CGP Part 7.2.10. You must include stabilization measure in the SWPPP per CGP Part 7.2.6.vii. You must, at a minimum, conduct a site inspection once every 14 calendar days and within 24 hours of a storm event that produces 0.25 inches of rain within a 24-hour period as per CGP Part 4.2 and City Ordinance 14-5-2-11.
3 | Silt fence and fiber rolls are missing from what is shown on the SWPPP map. Required mitigation: Re-install BMPs to reflect what is shown on the SWPPP map or modify the existing SWPPP map to reflect current conditions on the ground. Either ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage per CGP Part 2.1.4 or you must modify your SWPPP, including the site map, within 7 days if you make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPP per CGP Part 7.4.1.
4 | Washout was observed on bare soil and not in the available washout stations. Required mitigation: Remove and discard construction wastes as required per CGP Part 2.3.3. Direct wash water into a leak-proof container or a leak-proof and lined pit. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground as per CGP Part 2.3.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2022-09-01
Notes:
Violations from prior inspections include posting, BMPs, SWPPP, stabilization
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action