## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | Q16EA5000A |  | Project Name: |  | Kairos Power
NPDES Id. No. | NMR10033B/NMR1004XE |  | Location: |  | 5201 Hawking Dr. SE | [5 empty] | Pete Jacobsen | Stormwater Solutions
2022-08-23 |  | Owner? - NMR10033B |  |  |  | NMR1004XE |  |  |  |  | Klinger | Stephanie Maestas
Operator |  | Kairos Power, LLC |  |  |  | Kairos Power, LLC |  |  |  |  | 505-228-8567
Contact name & title |  | Lance Hagenbuch |  |  |  | Lara Gutierrez |  |  |  |  | petej@klingerllc.com
e-mail |  | hagenbuch@kairospower.com |  |  |  | gutierrez@kairospower.com
Contact Phone # |  | 510-230-3353 |  |  |  | 510-808-5265
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11am |  |  |  |  | Rain
Construction Phase: |  | Stabilization | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 80 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-08-21 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Posting of permit coverage was missing. Post signage of NOI permit coverage in a location clearly visible to the public CGP1.5. | [9 empty] | 2021-05-03
2 | The up-to-date SWPPP was not available onsite. The SWPPP must include current self-inspection reports and an accurate SWPPP map showing current BMPs and current area of disturbance per CGP 7.2.1 and 7.2.4. | [9 empty] | 2021-05-31
3 | Permit coverage lapsed from termination of NMR10033B on 2/18/2022 to issuance of new coverage NMR1004XE effective on 7/22/2022. Termination was certified by Estefanita Maestas of stormwatersolutionsllc4@gmail.com. Provide explanation for lapse in coverage, missing inspections, and delay in stabilization.
4 | Inactive areas must be stabilized within 14 days per CGP2.2.14.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes:
Sediment and erosion controls and self-inspection reports must continue until stabilization is accepted
by the City.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action