## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | Q16E5000D |  | Project Name: |  | Kairos Power Pond
NPDES Id. No. | NMR10069Y |  | Location: |  | 5201 Hawking Dr SE
2025-01-30 |  | Owner |  |  |  | Contractor
Operator |  | Kairos Power |  |  |  | Southwest Building and Development, LLC
Contact name & title |  | Mike Laufer |  |  |  | Jerry Gallegos
e-mail |  | mcintosh@kairospower.com |  |  |  | swfabrication@aol.com
Contact Phone # |  | 510-808-5262 |  |  |  | 505-920-8088
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | pond installed, pre stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | cloudy |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | N/A
Notes:
Stabilization needed if pond is complete.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action