## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E003C |  | Project Name: |  | Montage Unit 6
NPDES Id. No. | NMR10064U |  | Location: |  | Bobby Foster and University | [5 empty] | mikef@thewestway.com
2025-03-24 |  | Owner |  |  |  | Contractor
Operator |  | MDS Investments LLC |  |  |  | Guzman |  |  |  |  | mannybarrera@ravenswingconsulting.com
Contact name & title |  | Tom Schmidt |  |  |  | Eddie Gonzales
|  | tom@SC3development.com |  |  |  | eddie@guzmancs.com
Contact Phone # |  | 505-238-0700 |  |  |  | 505-452-0663
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1230-130pm |  |  |  | Rain
Construction Phase: |  | Grading, curbs | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 65 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-11-07 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs - The perimeter silt fencing needs to be reset as it has collapsed in several areas in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-02-24
Notes:
Heavy Equipment is being stored on the MDS Investment Stockpile lot. If this equipment is related to the development of Montage Unit 6, either the SWPPP map will need to be amended to include the area used to store equipment or the equipment moved to your property. MDS Investment LLC has included their NOI in the SWPPP.
The SWPPP is in a doc-box mounted on the back of the posting.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action