## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E003C |  | Project Name: |  | MDS Montage 6
NPDES Id. No. | NMR10062Y |  | Location: |  | University and Bobby Foster
2025-07-30 |  | Owner |  |  |  | Contractor
Operator |  | Cuesta Del Oro LLC |  |  |  | Twilight Homes
Contact name & title |  | Tim McNaney |  |  |  | Tim McNaney
e-mail |  | tmcnaney@twilighthomesnm.com |  |  |  | tmcnaney@twilighthomesnm.com
Contact Phone # |  | 505-975-7754 |  |  |  | 505-975-7754
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:45am |  |  |  | Rain
Construction Phase: |  | start of verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-07-03 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | There was no posting of your permit coverage on-site during the inspection in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5.
2 | The SWPPP and inspection reports were unavailable at the time of the inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and copies of all your inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. If an on-site location is unavailable to keep the SWPPP or inspection reports when no personnel are present, notice of the plan's location must be posted near the main entrance of your construction site.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The sales office could not make contact with the superintendent.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action