## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E003C |  | Project Name: |  | MDS Montage 6
NPDES Id. No. | NMR10062Y |  | Location: |  | University and Bobby Foster
2025-12-09 |  | Owner |  |  |  | Contractor
Operator |  | Cuesta Del Oro LLC |  |  |  | Twilight Homes
Contact name & title |  | Tim McNaney |  |  |  | Tim McNaney
e-mail |  | tmcnaney@twilighthomesnm.com |  |  |  | tmcnaney@twilighthomesnm.com
Contact Phone # |  | 505-975-7754 |  |  |  | 505-975-7754
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:30-11am |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-11-23 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Track-out - There is heavy sediment deposit on paved surfaces due to track-out from hauling dirt in violation of CGP Part 2.2.4. Required mitigation: Use appropriate stabilization techniques at all points that exit onto paved roads per CGP Part 2.2.4.b. Where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside of your site, remove the deposited sediment by the end of the same business day in which the track-out occurs or by the end of the next business day if the track-out occurs on a non-business day per CGP Part 2.2.4.d. Your are prohibited from hosing or sweeping tracked out material into any constructed or natural site drainage feature, storm drain inlet, or receiving water.
2 | Washout - Concrete washout is leaking from the washout container, and there are spots of washout occuring on bare soil in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be discharged on the ground.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | OK | Latest report Date: |  | 2025-11-17
Notes:
The posting and SWPPP are located at the very northwestern corner of Montage 6 (Bobby Foster construction entrance)
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action