## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E006_A |  | Project Name: |  | Mesa Del Sol Unit 3B
NPDES Id. No. | NMR1003AX |  | Location: |  | DeKooning Ave. & Motherwell Dr. SE
2022-02-04 |  | Owner |  |  |  | Contractor
Operator |  | Abrazo Homes
Contact name & title |  | Mackenzie Bishop |  |  |  | Mikaela Smith
e-mail |  | mackenzie@abrazohomes.com |  |  |  | mikaela@abrazohomes.com
Contact Phone # |  | 505-228-1401 |  |  |  | 505-301-4410
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: | 1:20 PM/1:35 PM |  |  |  | Rain
Construction Phase: |  | Home construction | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Rain |  | Temperature: ~ |  | 26 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-02-22 |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Remove and dispose of construction waste
2 | NPDES Posting required (no sign) Where is the Posting?
3 | Up-to-date SWPPP was not available onsite (location not noted on sign). Where is the SWPPP?
4 | Sediment in north ally marginal, needs removed before it gets worse.
Yes
4 | Discharge off site? (Y/N) |  |  | Yes | Where is SWPPP and Posting? |  |  |  |  | No
3 | Self Inspection Reports |  |  |  | Latest report Date:
Notes:
Snowing at time of inspection, couldn't find any posting or indication of SWPPP location, only 6 houses left framed ready for stucco but no washout containers, some sediment in north alley, some waste paper /wrapers on the ground with lumber
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes 505 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action