## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E006A_WW |  | Project Name: |  | MDS Unit 4
NPDES Id. No. | NMR1004HK |  | Location: |  | Strand Loop and O'Keefe Ave
2025-03-24 |  | Owner |  |  |  | Contractor
Operator |  | Westway Homes
Contact name & title |  | Michael Fietz
e-mail |  | mikef@thewestway.com
Contact Phone # |  | 505-379-5388
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1230pm |  |  |  | Rain
Construction Phase: |  | >75% houses complete, still some vacant lots | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 65 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP for Westway Homes Mesa Del Sol Unit 4 and the related inspection reports are missing the certification signatures of the operator in violation of CGP Parts 4.7.2 and 7.2.10. The latest inspection report included in the SWPPP is dated 1/9/2025 in violation of CGP Part 4.7.3. Required mitigation: Your signatory must sign and date your SWPPP and all inspection reports in accordance with CGP Appendix G, Part G.11 per CGP Parts 4.7.2 and 7.2.10. You must keep a copy of all inspection reports at the site or at an easily accessible location, so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-01-09
Notes:
The SWPPPs are at 4222 Dekooning Ave SE.
The Delegation of Authority page is blank.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action