## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E006C |  | Project Name: |  | Montage Unit 5
NPDES Id. No. | NMR10062N |  | Location: |  | Bobby Foster and University | [5 empty] | mikef@thewestway.com
2025-03-24 |  | Owner |  |  |  | Contractor
Operator |  | Titan Montage 5 |  |  |  | Guzman |  |  |  |  | mannybarrera@ravenswingconsulting.com
Contact name & title |  | Brian Patterson |  |  |  | Eddie Gonzales
|  | bpatterson@titan-development.com |  |  |  | eddie@guzmancs.com
Contact Phone # |  | 505-238-0700 |  |  |  | 505-452-0663
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1145am |  |  |  | Rain
Construction Phase: |  | Beginning verticals, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 65 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2025-11-07 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs - The perimeter silt fencing along the western and southern borders have collapsed and need maintenance/repair/replacement in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-03-10
Notes:
Amend the SWPPP as properties are sold or operational control is transferred.
The SWPPP is in a doc-box mounted on the back of the posting.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action