## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E006C_A |  | Project Name: |  | Mesa Del Sol Montage 5
NPDES Id. No. | NMR 1006Y8 |  | Location: |  | Diebenkorn Dr and Scholer Ave SE
2025-07-30 |  | Owner |  |  |  | Contractor
Operator |  | Abrazo Homes
Contact name & title |  | Mackenzie Bishop
e-mail |  | mackenzie@abrazohomes.com
Contact Phone # |  | 505-269-0915
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-07-03 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The SWPPP and inspection reports were not available at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of the current SWPPP and all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
2 | Washout - There is a large pile of concrete washout on bare ground in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and line pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
According to tax records, the property still belongs to Titan Montage 5 LLC
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action