## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E006C_DR |  | Project Name: |  | Mesa Del Sol Montage 5
NPDES Id. No. | NMR 1007BQ |  | Location: |  | Scholer Ave and Groman Ave SE
2025-07-30 |  | Owner |  |  |  | Contractor
Operator |  | DR Horton
Contact name & title |  | Tom Totaro
e-mail |  | tjtotaro@drhorton.com
Contact Phone # |  | 505-797-4245
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-07-03 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | None - Posting and SWPPP were placed on-site just prior to inspection.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
According to tax records, property is still owned by Titan Montage 5 LLC
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action