## 26.03.13Form
City of Albuquerque | [7 empty] | Inspection: | Weather: | Violation: | Reports: | Discharge: | ROW: | Yes/No/NA
Stormwater, Erosion, and Sediment Control | [7 empty] | Inspection | Weather | Violation | Reports | Discharge | ROW Type | Yes/No/NA
Construction Site Inspection Report | [13 empty] | Yes
General Information | [7 empty] | Pre-Construction | Ice | None | Yes | Shadow | Other | No
ESC File #: |  | R16E006C |  | Project Name: | Montage Unit 5 |  |  | Routine | Hail | NOI | No | Yes | Sidewalk | N/A
ABQ-PLAN #: |  | None |  | Project Address: | Bobby Foster Blvd and University Blvd |  |  | Follow-up | Snow | Posting | Requested | No | Street
NPDES ID #: |  | NMR10062N |  | Inspection Type: | Routine |  |  | 311/Complaint | Clear | SWPPP | Out-of-date |  | Storm Drain Inlet
2026-03-27 |  | Owner |  |  | Contractor |  |  | Storm Event | Rain | BMPs | Unsigned |  | Drainage Ditch
Operator: |  | Titan Montage 5 LLC |  |  | Guzman |  |  | Post Storm Even >0.25" | Clear/Windy | Sediment |  |  | Arroyo
Contact Name: |  | Brian Paterson |  |  | Eddie Gonzales |  |  |  | Windy | Washout |  |  | Private Property
Contact e-mail: |  | bpatterson@titan-development.com |  |  | eddie@guzmancs.com |  |  |  | Cloudy | Litter |  |  | N/A
Contact Phone: |  | 505-238-0700 |  |  | 505-452-0663 |  |  |  | Sleet | Porta-potty
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 3/26-27/2026 | Time of Inspection: | 12pm |  |  | Stabilization
NPDES Posting? |  | No | SWPPP? | No | Notice of Intent? | Yes
Self-Inspection Reports? |  |  |  | Date of last report:
Weather during inspection: |  |  | Clear/Windy | Estimated date of last storm 0.25" or greater: |  | 2026-01-25 | Snow
Temperature: ~ |  | 85 | Construction Phase: | Pond
Discharge off-site? |  | No | ROW: | ROW Type
Item # | Violation Category | Deficiency/Corrective Action
1 | Washout | There are multiple areas of concrete washout on bare ground or around washout containers in violation of CGP Part 2.3.4. The stockpile area on the northern portion of the property has accumulated debris piles being used for washout, and other developers have washout on the ground around their washouts. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Page 2
City of Albuquerque
Stormwater, Erosion, and Sediment Control
Construction Site Inspection Report - Page 2
General Information
ESC File #: |  | R16E006C |  | Project Name: | Montage Unit 5
ABQ-PLAN #: |  | None |  | Project Address: | Bobby Foster Blvd and University Blvd
NPDES ID #: |  | NMR10062N |  | Inspection Type: | Routine
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 3/26-27/2026 | Time of Inspection: | 12pm
Item # | Violation Category | Deficiency/Corrective Action
1 | Violation
2 | NOI
3 | Posting
4 | SWPPP
5 | BMPs
6 | Sediment
7 | Washout
8 | Litter
9 | Porta-potty
10 | Stabilization
11
12
13
14
15
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov
pg 2