## 26.03.13Form
City of Albuquerque | [7 empty] | Inspection: | Weather: | Violation: | Reports: | Discharge: | ROW: | Yes/No/NA
Stormwater, Erosion, and Sediment Control | [7 empty] | Inspection | Weather | Violation | Reports | Discharge | ROW Type | Yes/No/NA
Construction Site Inspection Report | [13 empty] | Yes
General Information | [7 empty] | Pre-Construction | Ice | None | Yes | Shadow | Other | No
ESC File #: |  | R16E006C_A |  | Project Name: | Mesa Del Sol Montage 5 |  |  | Routine | Hail | NOI | No | Yes | Sidewalk | N/A
ABQ-PLAN #: |  | SWQ-2025-00045 |  | Project Address: | Diebenkorn Dr and Scholer Ave SE |  |  | Follow-up | Snow | Posting | Requested | No | Street
NPDES ID #: |  | NMR1006Y8 |  | Inspection Type: | Routine |  |  | 311/Complaint | Clear | SWPPP | Out-of-date |  | Storm Drain Inlet
2026-03-30 |  | Owner |  |  | Contractor |  |  | Storm Event | Rain | BMPs | Unsigned |  | Drainage Ditch
Operator: |  | Abrazo Homes | [5 empty] | Post Storm Even >0.25" | Clear/Windy | Sediment |  |  | Arroyo
Contact Name: |  | Mackenzie Bishop | [6 empty] | Windy | Washout |  |  | Private Property
Contact e-mail: |  | mackenzie@abrazohomes.com | [6 empty] | Cloudy | Litter |  |  | N/A
Contact Phone: |  | 505-269-0915 | [6 empty] | Sleet | Porta-potty
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 3/26-27/2026 | Time of Inspection: | 12pm |  |  | Stabilization
NPDES Posting? |  | Yes | SWPPP? | No | Notice of Intent? | No
Self-Inspection Reports? |  |  | No | Date of last report: | N/A
Weather during inspection: |  |  | Clear/Windy | Estimated date of last storm 0.25" or greater: |  | 2026-01-25 | Snow
Temperature: ~ |  | 85 | Construction Phase: | Verticals, grading
Discharge off-site? |  | No | ROW: | N/A
Item # | Violation Category | Deficiency/Corrective Action
1 | Washout | The concrete washout container is leaking contaminated wash water onto the ground in violation of CGP Part 2.3.4. There is also a pile of concrete washout adjacent to the container. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
2 | SWPPP | The SWPPP and inspection reports were not available at the time of the inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of the current SWPPP and all inspection reports at the site or at an easily accessible location so they can be made immediately available during the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
3 | Sediment | There is a dirt ramp in the curb and across a public sidewalk on Scholer Ave in violation of CGP Part 2.2.4. Required mitigation: Restrict vehicle use to properly designated exit points, use appropriate stabilization techniques at all points that exit onto paved roads, and where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas of your site, remove the deposited sediment the same day it occurs per CGP Part 2.2.4.
Notes: | The posting is on Gatch Alley.
Dirt ramps on sidewalks and in curbs can also present a safety hazard.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Page 2
City of Albuquerque
Stormwater, Erosion, and Sediment Control
Construction Site Inspection Report - Page 2
General Information
ESC File #: |  | R16E006C_A |  | Project Name: | Mesa Del Sol Montage 5
ABQ-PLAN #: |  | SWQ-2025-00045 |  | Project Address: | Diebenkorn Dr and Scholer Ave SE
NPDES ID #: |  | NMR1006Y8 |  | Inspection Type: | Routine
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 3/26-27/2026 | Time of Inspection: | 12pm
Item # | Violation Category | Deficiency/Corrective Action
1 | Violation
2 | NOI
3 | Posting
4 | SWPPP
5 | BMPs
6 | Sediment
7 | Washout
8 | Litter
9 | Porta-potty
10 | Stabilization
11
12
13
14
15
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov
pg 2