## 26.03.13Form
City of Albuquerque | [7 empty] | Inspection: | Weather: | Violation: | Reports: | Discharge: | ROW: | Yes/No/NA
Stormwater, Erosion, and Sediment Control | [7 empty] | Inspection | Weather | Violation | Reports | Discharge | ROW Type | Yes/No/NA
Construction Site Inspection Report | [13 empty] | Yes
General Information | [7 empty] | Pre-Construction | Ice | None | Yes | Shadow | Other | No
ESC File #: |  | R16E006C_DR |  | Project Name: | Mesa Del Sol Montage 5 |  |  | Routine | Hail | NOI | No | Yes | Sidewalk | N/A
ABQ-PLAN #: |  | SWQ-2025-00039 |  | Project Address: | Scholer Ave and Gorman Ave SE |  |  | Follow-up | Snow | Posting | Requested | No | Street
NPDES ID #: |  | NMR1007BQ |  | Inspection Type: | Routine |  |  | 311/Complaint | Clear | SWPPP | Out-of-date |  | Storm Drain Inlet
2026-03-30 |  | Owner |  |  | Contractor |  |  | Storm Event | Rain | BMPs | Unsigned |  | Drainage Ditch
Operator: |  | DR Horton | [5 empty] | Post Storm Even >0.25" | Clear/Windy | Sediment |  |  | Arroyo
Contact Name: |  | Tom Totaro | [6 empty] | Windy | Washout |  |  | Private Property
Contact e-mail: |  | tjtotaro@drhorton.com | [6 empty] | Cloudy | Litter |  |  | N/A
Contact Phone: |  | 505-797-4245 | [6 empty] | Sleet | Porta-potty
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 3/26-27/2026 | Time of Inspection: | 12pm |  |  | Stabilization
NPDES Posting? |  | Yes | SWPPP? | Yes | Notice of Intent? | Yes
Self-Inspection Reports? |  |  | Yes | Date of last report: | 2026-03-16
Weather during inspection: |  |  | Clear/Windy | Estimated date of last storm 0.25" or greater: |  | 2026-01-25 | Snow
Temperature: ~ |  | 85 | Construction Phase: | Verticals, foundations
Discharge off-site? |  | No | ROW: | N/A
Item # | Violation Category | Deficiency/Corrective Action
1 | Washout | The washout area has concrete washout surrounding the pit in violation of CGP Part 2.3.4.. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Notes:
The SWPPP is mounted to the back of the posting on Bultman Alley.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Page 2
City of Albuquerque
Stormwater, Erosion, and Sediment Control
Construction Site Inspection Report - Page 2
General Information
ESC File #: |  | R16E006C_DR |  | Project Name: | Mesa Del Sol Montage 5
ABQ-PLAN #: |  | SWQ-2025-00039 |  | Project Address: | Scholer Ave and Gorman Ave SE
NPDES ID #: |  | NMR1007BQ |  | Inspection Type: | Routine
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 3/26-27/2026 | Time of Inspection: | 12pm
Item # | Violation Category | Deficiency/Corrective Action
1 | Violation
2 | NOI
3 | Posting
4 | SWPPP
5 | BMPs
6 | Sediment
7 | Washout
8 | Litter
9 | Porta-potty
10 | Stabilization
11
12
13
14
15
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov
pg 2