## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E006C_R |  | Project Name: |  | RMH at Mesa Del Sol Unit 5
NPDES Id. No. | NMR10073L |  | Location: |  | Scholer Ave and Gilpin Dr SE
2025-07-25 |  | Owner |  |  |  | Contractor
Operator |  | Richmond American Homes of New Mexico
Contact name & title |  | Troy Crutchfield
e-mail |  | troy.crutchfield@mdch.com
Contact Phone # |  | 505-228-1401
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:30pm |  |  |  | Rain
Construction Phase: |  | Verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-07-03 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports were not available at the time of inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and all inspection reports at the site or at an easily accessible location so that it can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
2 | The permit coverage posting sign was leaning up against the construction office in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way.
3 | The BMPs (silt fence) were not installed according to the approved ESC Plan submitted to the City in violation of CGP Part 2.1.3. Required mitigation: Complete installation of stormwater controls by the time each phase of construction activities has begun per CGP Part 2.1.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2025-07-17
Notes:
The latest inspection report was emailed, but not available on-site.
Please ensure that the sediment in the streets is swept up before the first house is occupied.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action