## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E006C_R |  | Project Name: |  | RMH at Mesa Del Sol Unit 5
NPDES Id. No. | NMR10073L |  | Location: |  | Scholer Ave and Gilpin Dr SE
2025-12-08 |  | Owner |  |  |  | Contractor
Operator |  | Richmond American Homes of New Mexico
Contact name & title |  | Troy Crutchfield
e-mail |  | troy.crutchfield@mdch.com
Contact Phone # |  | 505-228-1401
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1:30pm |  |  |  | Rain
Construction Phase: |  | Verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-11-23 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | BMPs - Intlet protection needs to be repaired/maintained at several locations in violation of CGP Part 2.2.10. Required mitigation: Clean, or remove and replace, the inlet protection measures as sediment accumulates, the filter becomes clogged, and/or performance is compromised per CGP Part 2.2.10.b. Where there is evidence of sediment accumulation adjacent to the inlet protection measure, remove the deposited sediment by the end of the same business eday in which it is found or by the end of the following business day if removal by the same business day is not feasible.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | OK | Latest report Date: |  | 2025-11-19
Notes:
The posting and the SWPPP are at the mobile construction office next to the model home/office.
The washout pit needs maintenance (lining and overflow).
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action