## 26.03.13Form
City of Albuquerque | [7 empty] | Inspection: | Weather: | Violation: | Reports: | Discharge: | ROW: | Yes/No/NA
Stormwater, Erosion, and Sediment Control | [7 empty] | Inspection | Weather | Violation | Reports | Discharge | ROW Type | Yes/No/NA
Construction Site Inspection Report | [13 empty] | Yes
General Information | [7 empty] | Pre-Construction | Ice | None | Yes | Shadow | Other | No
ESC File #: |  | R16E097C |  | Project Name: | Mesa Del Sol by Woodbury |  |  | Routine | Hail | NOI | No | Yes | Sidewalk | N/A
ABQ-PLAN #: |  | SWQ-2025-00062 |  | Project Address: | Tract A University Blvd SE |  |  | Follow-up | Snow | Posting | Requested | No | Street
NPDES ID #: |  | NMR1007KC |  | Inspection Type: | Routine |  |  | 311/Complaint | Clear | SWPPP | Out-of-date |  | Storm Drain Inlet
2026-03-23 |  | Owner |  |  | Contractor |  |  | Storm Event | Rain | BMPs | Unsigned |  | Drainage Ditch
Operator: |  | MDS Flats QOZB, LLC |  |  | Pavilion Construction, LLC |  |  | Post Storm Even >0.25" | Clear/Windy | Sediment |  |  | Arroyo
Contact Name: |  | Jason Wedlick |  |  | Chris Tuggle |  |  |  | Windy | Washout |  |  | Private Property
Contact e-mail: |  | j_wedlick@woodburycorp.com |  |  | ctuggle@pavilionconstruction.com |  |  |  | Cloudy | Litter |  |  | N/A
Contact Phone: |  | 801-485-7770 |  |  | 505-403-1722 |  |  |  | Sleet | Porta-potty
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 2026-03-19 | Time of Inspection: | 11:45am |  |  | Stabilization
NPDES Posting? |  | Yes | SWPPP? | Yes | Notice of Intent? | Yes
Self-Inspection Reports? |  |  | Out-of-date | Date of last report: | 2026-02-04
Weather during inspection: |  |  | Clear | Estimated date of last storm 0.25" or greater: |  | 2026-01-25 | Snow
Temperature: ~ |  | 85 | Construction Phase: | Verticals, utilities, foundations
Discharge off-site? |  | No | ROW: | N/A
Item # | Violation Category | Deficiency/Corrective Action
1 | SWPPP | The SWPPP has not been certified by the owner in violation of CGP Part 7.2.10. Required mitigation: Your signatory must sign and date your SWPPP in accordance with CGP Appendix G, Part G.11.
2 | Washout | The concrete washout container is overloaded and leaking, and there is a pile of concrete washout on bare soil in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Notes:
The SWPPP is in the construction office south of the Community Office building next to the "tower". (South of University and Stryker)
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Page 2
City of Albuquerque
Stormwater, Erosion, and Sediment Control
Construction Site Inspection Report - Page 2
General Information
ESC File #: |  | R16E097C |  | Project Name: | Mesa Del Sol by Woodbury
ABQ-PLAN #: |  | SWQ-2025-00062 |  | Project Address: | Tract A University Blvd SE
NPDES ID #: |  | NMR1007KC |  | Inspection Type: | Routine
COA Inspector: |  | Chancellor English |  | Date of Inspection: | 2026-03-19 | Time of Inspection: | 11:45am
Item # | Violation Category | Deficiency/Corrective Action
1 | Violation
2 | NOI
3 | Posting
4 | SWPPP
5 | BMPs
6 | Sediment
7 | Washout
8 | Litter
9 | Porta-potty
10 | Stabilization
11
12
13
14
15
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov
pg 2