## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16E101 |  | Project Name: |  | Encanto Apartments
NPDES Id. No. | NMR1004QH |  | Location: |  | 5501 University Blvd SE | [5 empty] | mikef@thewestway.com
2024-05-16 |  | Owner |  |  |  | Contractor
Operator |  | Encanto QOZB LLC |  |  |  | Pavilion Construction |  |  |  |  | mannybarrera@ravenswingconsulting.com
Contact name & title |  | Clayton Damron |  |  |  | Paul Lamb
|  | cdamron@cruachancapital.com |  |  |  | plamb@pavilionconstruction.com
Contact Phone # |  | 972-665-8792 |  |  |  | 505-346-0085
COA Inspector |  | Chance English |  |  |  | Start/End Time: |  | 10:30am |  |  |  | Rain
Construction Phase: |  | Verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Rain |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-04-01 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The NOI is not up to date and is in the name of a previous owner in violation of CGP Part 7.2.11. The self-inspection reports are missing both operators' signatures in violation of CGP Part 4.7.2. Required mitigation: Once you are authorized for coverage under the CGP, you must include a copy of your NOI submitted to the EPA along with correspondence between you and the EPA related to permit coverage per CGP Part 7.2.11. Each inspection report must be signed by the operator's signatory in accordance with CGP Appendix G, Part G.11 per CGP Part 4.7.2.
2 | There is concrete washout on the ground in violation of CGP Part 2.3.4. Required mitigation: You must direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
3 | There is a pile of dirt that was deposited on Strand Loop Rd in violation of CGP Part 2.2.4. Required mitigation: Where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside your site, remove the sediment by the end of the same business day in which the track-out occurs per CGP Part 2.2.4.d.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-05-15
Notes:
If Mesa Apartments, LLC is no longer affiliated with the project, they need to terminate their permit coverage
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chance English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action