## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16EA1004 |  | Project Name: |  | Mesa Del Sol Self storage
NPDES Id. No. | NMR1006UR |  | Location: |  | 5500 Turing Dr. SE
2025-09-16 |  | Owner |  |  |  | Contractor
Operator |  | MDS Storage, LLC |  |  |  | Bottom Line Construction
Contact name & title |  | Kegan Stephens |  |  |  | Todd Colman
e-mail |  | Kegan@stopabq.com |  |  |  | todd@blcm.com
Contact Phone # |  | 505-290-9837 |  |  |  | 505-269-7481
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 130pm |  |  |  | Rain
Construction Phase: |  | structures | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-08-27 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | SWPPP - There were no inspection reports available on-site during the inspection in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The SWPPP is located in a closed storage bay in the building to the right of the construction exit along with the master plans. Enter from the side opposite the construction exit.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action