## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16EA1004 |  | Project Name: |  | Mesa Del Sol Self storage
NPDES Id. No. | NMR1006UR |  | Location: |  | 5500 Turing Dr. SE
2025-12-26 |  | Owner |  |  |  | Contractor
Operator |  | MDS Storage, LLC |  |  |  | Bottom Line Construction
Contact name & title |  | Kegan Stephens |  |  |  | Todd Colman
e-mail |  | Kegan@stopabq.com |  |  |  | todd@blcm.com
Contact Phone # |  | 505-290-9837 |  |  |  | 505-269-7481
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:45am |  |  |  | Rain
Construction Phase: |  | structures | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-11-20 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | SWPPP - There were no inspection reports available on-site during the inspection in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2 | Sediment - There is a dirt ramp in the curb at the construction exit in violation of CGP Part 2.2.4. Dirt ramps are not allowed in City streets per City Ordinance §6-11-6. Required mitigation: Use appropriate stabilization techniques at all points that exit onto paved roads per CGP Part 2.2.4. No person shall blow or otherwise cause dirt, leaves, or other organic or inorganic material to move from any private property to any public property or into the MS4 per City Ordinance §6-11-6(B)(4).
3 | BMPs - The stabilized construction exit requires maintenance or repair in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The SWPPP is located in a closed storage bay in the building to the right of the construction exit along with the master plans. Enter from the side opposite the construction exit.
Remove the dirt ramp and replace with rock. Clean sediment from construction exit.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action