## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | R16EA1004 |  | Project Name: |  | Mesa Del Sol Self storage
NPDES Id. No. | NMR1006UR |  | Location: |  | 5500 Turing Dr. SE
2025-05-14 |  | Owner |  |  |  | Contractor
Operator |  | MDS Storage, LLC |  |  |  | Bottom Line Construction
Contact name & title |  | Kegan Stephens |  |  |  | Todd Colman
e-mail |  | Kegan@stopabq.com |  |  |  | todd@blcm.com
Contact Phone # |  | 505-290-9837 |  |  |  | 505-269-7481
COA Inspector |  | James Hughes |  |  |  | start |  | 11:20AM |  |  |  | Rain
Construction Phase: | [11 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? | [5 empty] | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-04 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NOI - The property owners NOI wasn't approved by the City in Violation of City Ordinance § 14-5-2-11(A). Required Mitigation: The property owner’s NOI and ESC Plan must be submitted to the City of Albuquerque for review and approval per Albuquerque’s Erosion and Sediment Control (ESC) ordinance § 14-5-2-11(A).
2 | Sediment had been discharged from the site and deposited in the adjacent street, Turing Dr., and not removed within 24 hours in violation of CGP 2.2.4.d. Required mitigation: Remove sediment deposited in the streets by the end of the same business day. Remove the sediment by sweeping, shoveling, or vacuuming these surfaces or using other similarly effective means of sediment removal. You are prohibited from hosing or sweeping sediment per CGP 2.2.4.d.
3 | BMPs - The stabilized construction exit was missing, in violation of CGP 2.2.4. Consequently, stormwater controls were not implemented and maintained to minimize the discharge of pollutants from this site, in violation of CGP 2.1. Required Mitigation: If, at any time, you find that a stormwater control device requires routine Maintenance, you must immediately initiate the necessary maintenance work and complete it by the close of the next business day. When the problem requires a new or replacement control, such as the missing Construction Exit, install the new or modified control and make it operational no later than seven (7) calendar days from the time of discovery per CGP 5.2.1. Dirt ramps are not allowed on the paved street.
2.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | Yes
4 | Self Inspection Reports |  |  | ok | Latest report Date: |  | 2025-05-08
Notes:
The SWPPP was in the Conex.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action