## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | U13E001 |  | Project Name: |  | Tract 7 MDS
NPDES Id. No. |  |  | Location: |  | 9601 Broadway Blvd SE
2022-04-01 |  | Owner |  |  |  | Contractor
Operator |  | MDS Investments, LLC |  |  |  | Guzman Construction Solutions
Contact name & title |  | Kyle Bodine |  |  |  | Rudy Guzman
e-mail |  | Kyle@sc3intl.com |  |  |  | rudy@guzmancs.com
Contact Phone # |  | 681-9932 |  |  |  | 505-459-3128
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10-11am |  |  |  | Rain
Construction Phase: |  | Excavation/grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 58 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2022-03-22 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Three prior areas of concern have been mitigated at the time of this inspection, including ESC Plan and NOI approval, Posting, and up-to-date SWPPP availabile on site. However there still aren't any BMPs on site. In accordance with the established escalation procedures an additional 10 days will be allowed to complete the BMPs since the operators have been cooperative and have made significant progress in mitigating 3 out of 4 of the original voilations. If the BMPs are not installed by 4/11/2021 a fine of $500/day will be imposed for each of the 19 days since the fine for the first day on 3/23/2022.
2.1 | Discharge off site? (Y/N) |  |  | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | n/a
The entire site was cleared, graded and compacted, one stockpile of earth 15' tall by 300' long was present at the first inspection on 3/14/2022 along with a manufactured building. A 40'x90' stack of concrete traffic barriers has been onsite for about 4 years with minimal land disturbance. A second dirt pile was added the next day. There hadn't been any noticeable activity for 15 days at the time of the third inspection on 4/1/2022.
On 4/1/2022 I met with Lupita Pena and Eddie Gonzales at Guzman Construction office in the MDS Aperture building to review the SWPPP, violation status, and escalation process. The SWPPP containbed the map, Operator Certifications, NOIs, and a copy of the 2022 CGP and was generally up-to-date. The NOI for MDS Investments LLC was certified on 3/28/2022.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action