## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | U13E001 |  | Project Name: |  | Tract 7 MDS
NPDES Id. No. | NMR1004MM |  | Location: |  | 9601 Broadway Blvd SE
2022-04-14 |  | Owner |  |  |  | Contractor
Operator |  | MDS Investments, LLC |  |  |  | Guzman Construction Solutions
Contact name & title |  | Kyle Bodine |  |  |  | Rudy Guzman
e-mail |  | Kyle@sc3intl.com |  |  |  | rudy@guzmancs.com
Contact Phone # |  | 681-9932 |  |  |  | 505-459-3128
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: | 5PM |  |  |  | Rain
Construction Phase: |  | Excavation/grading | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2022-03-22 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | There hasn't been any noticeable activity in 29 days. Stabilize areas that are to remain inactive for 14 days or more per CGP2.2.14.a. The Arid and Semi -arid Exceptions don't apply this time of the year so Seed & Hydromulch would be appropriate. Alternatively Gravel is frequently used to satisfy the Final Stabilization Criteria for Construction Material Storage Yards.
2.1 | Discharge off site? (Y/N) |  |  | no
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes:
The Silt Fence was in place around the perimeter though it needed maintenance in some spots
Still just 2 stockpiles.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action