## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | U13E001 |  | Project Name: |  | 9601 Broadway SE Stockpile
NPDES Id. No. | NMR1004MM |  | Location: |  | 9601 Broadway SE
2024-04-29 |  | Owner |  |  |  | Contractor
Operator |  | MDS Investments |  |  |  | Guzman
Contact name & title |  | Rudy Guzman |  |  |  | Rudy Guzman
e-mail |  | rudy@guzmancs.com |  |  |  | rudy@guzmancs.com
Contact Phone # |  | 505-459-3128 |  |  |  | 505-459-3128
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-04-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None - Stabilized (Transferred to Industrial Permit and to DMD)
2
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | NA | Latest report Date: |  | NA
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action